## Gantt
Altera University Donation — Project Gantt (~3-month FPGA campaign)
Cross-Architecture Infrastructure Drift: Extending GPU-Validated Drift Measurement to FPGA-Based AI Inference (2× DE10-Agilex, CNR–ICAR Palermo)
Project-relative weeks (W1 = boards received & approved). Delivery window: ~2–3 months. Two boards run measurement + development in parallel.
Task | Description | WEEK (project weeks 1–13)
| Month | Month 1 |  |  |  | Month 2 |  |  |  | Month 3
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
T0 | Management, COI compliance & customs/custody (CNR–ICAR)
T1 | Board bring-up & toolchain (FPGA AI Suite) | bar: Month 1 1 to Month 1 4
1.1 | DE10-Agilex setup; PCIe design example deployed (both boards) | bar: Month 1 1 to Month 1 3
1.2 | Model selection (classifier ↔ AI Suite supported layer set) | bar: Month 1 2 to Month 1 4
T2 | Single-board drift measurement (RQ1, RQ3) | bar: Month 1 4 to Month 3 9
2.1 | Deploy classifier; measure output/safety drift on board | bar: Month 1 4 to Month 2 7
2.2 | Characterize static-schedule determinism vs GPU variation | bar: Month 2 6 to Month 3 9
T3 | FPGA-to-FPGA variance study (board-to-board drift) | bar: Month 2 5 to Month 3 10
3.1 | Run identical workload on both boards; bit-identity check | bar: Month 2 5 to Month 2 8
3.2 | Quantify any board-to-board variance as drift source | bar: Month 2 8 to Month 3 10
T4 | Portability Risk Index extension (RQ2) | bar: Month 2 7 to Month 3 12
4.1 | Fit GPU→FPGA into PRI; test cross-architecture transfer | bar: Month 2 7 to Month 3 11
4.2 | Determine: PRI predicts, or new drift category? | bar: Month 3 10 to Month 3 12
T5 | Deliverables, release & dissemination | bar: Month 2 6 to Month 3 13
5.1 | Extended DriftBench dataset + updated PRI (Apache-2.0/MIT) | bar: Month 3 9 to Month 3 13
5.2 | GPU/FPGA deployment guidelines; MLSys 2027 paper prep (downstream) | bar: Month 3 10 to Month 3 13
Key milestone (W4): |  | Month 1 1: Both boards bringing up the PCIe AI-Suite example with a layer-set-compatible model → drift measurement can begin.
Two-board rationale: |  | Month 1 1: Two boards enable the FPGA-to-FPGA variance study (do identical boards give bit-identical outputs?) and parallel measurement + development across the campaign.
Minimum deliverable: |  | Month 1 1: The self-contained RQ3 result — does a deterministic, statically-scheduled FPGA path reduce output drift vs GPU non-determinism — is achievable on one board even if the two-board variance study or PRI extension slips. W13 delivers the first public dataset + results; the MLSys 2027 paper is a downstream output on its own deadline.
Legend
Board bring-up & toolchain (FPGA AI Suite)
Single-board drift measurement (RQ1, RQ3)
FPGA-to-FPGA variance study
Portability Risk Index extension (RQ2)
Management / deliverables / release
Summary / theme bar (lighter shade)
◆ Milestone / deliverable

## Deliverables
Deliverables
Code | Due (week) | Title | Type | Confidentiality
D1.1 | 4 | Both DE10-Agilex boards bring up PCIe AI-Suite example; model selected | setup + report | public
D2.1 | 9 | Single-board FPGA drift measurement (output + safety, determinism characterized) | dataset + report | public
D3.1 | 10 | FPGA-to-FPGA variance result (board-to-board bit-identity) | dataset + report | public
D4.1 | 12 | PRI extended with FPGA support; cross-architecture transfer verdict | model + report | public
D5.1 | 13 | Extended public DriftBench dataset with FPGA measurements (Apache-2.0/MIT) | code + data | public
D5.2 | 13 | GPU/FPGA deployment guidelines; MLSys 2027 paper prep (downstream output) | report + paper | public